## Sheet1
PROJECT: Peru-Mexico, North Main Street over the Androscoggin River (Bridge No. 2019) |  |  |  |  | WIN: 18498.00
Alternative D: 840' Bridge Replacement Alternative Deck Area: 840’ total length x 40.25' width = 33,810 SF 5 Span Option
ESTIMATED BY: DMK
Unit Cost Reference:
SUPERSTRUCTURE: |  | 33810 | SF | x | 120 | = | 4058000 | Rumford Bid Tab Super Cost/SF = $122 (Average of 3 low bids). Low bid unit cost of 111 $/sf.
ABUTMENTS: |  | 2 | EA | x | 550000 | = | 1100000 | Assume full height abuts on piles. Say 600 k for abutments. Assume larger cost since 1 abutments close to RR.
PIERS: |  | 4 | EA | x | 500000 | = | 2000000 | 3 Piers @ $550,000 per pier. Reference Rumford average pier cost.
PIER COFFERDAMS: |  | 2 | EA | x | 200000 | = | 400000 | Ref Rumford Martin Bid Tabs. Say 2 Piers in the water require cofferdam.
STRUCTURAL EXCAVATION: ABUTMENTS |  | 600 | CY | x | 40 | = | 24000 | Excavation cost for piers assumed in pier unit cost.
RIPRAP: |  | 0 | CY | x |  | = | 0
EXISTING BRIDGE REMOVAL: |  | 13200 | SF | x | 30 | = | 396000 | Ref Rumford Martin Bid Tabs. Average of 3 bids is $375,000
DETOUR AND/OR TEMPORARY BRIDGE: |  | 0 | LS | x |  | = | 0
INCENTIVE ALLOWANCE: |  |  |  |  | N/A | = | 0
MISCELLANEOUS (TCP'S, FIELD OFFICE, ETC.): |  |  |  |  | 10% | = | 798000
MOBILIZATION: |  |  |  |  | 10% | = | 798000
STRUCTURE SUBTOTAL | [5 empty] | = | 9580000 | Bridge Cost per SF |  |  | 283.3481
APPROACHES: |  | 1500 | LF | x | 600 | = | 900000 | 1500 lf is for both approaches.
RETAINING WALL STRUCTURES: |  | 3000 | SF | x | 40 | = | 120000 | Based on Kittery Average of 65$/sf for 1600 sf. Say 40 due to large volume and no rock excavation. Say 600 $/lf due to height of fill required.
MISCELLANEOUS: |  |  |  |  | 10% | = | 90000
MOBILIZATION: |  |  |  |  | 10% | = | 90000
APPROACHES SUBTOTAL | [5 empty] | = | 1200000
TOTAL CONSTRUCTION COST | [5 empty] | = | 10780000 | Preliminary Percentage: | Preliminary Value: | Manual Value Override: | NOTE: Enter PE and CE percentage and value override (if needed) in green cells. Do NOT enter override values for both PE and CE.
PRELIMINARY ENGINEERING: |  |  |  |  | 8% | = | 850000 | 8% | 865000 | 850000
RIGHT OF WAY: | [5 empty] | = | 190000
CONSTRUCTION ENGINEERING: |  |  |  |  | 8% | = | 850000 | 8% | 865000 | 850000
OTHER: | [5 empty] | = | 0 | Use 8% & 8% Based on Rumford Martin and Steep Falls Values
TOTAL PROJECT COST | [5 empty] | = | 12700000