**STATE OF MAINE**

**Governor’s Office of Policy Innovation and the Future**



**RFP# 202409168**

**Climate Vulnerability Assessment of State Assets**

|  |  |
| --- | --- |
| **RFP Coordinator** | *All communication regarding the RFP must be made through the RFP Coordinator identified below*.**Name:** Hannah Silverfine **Title:** Climate Risk Management Project Coordinator**Contact Information:** hannah.silverfine@maine.gov  |
| **Submitted Questions Due** | *All questions must be received by the RFP Coordinator identified above by:***Date:** October 4, 2024, no later than 11:59 p.m., local time |
| **Proposal Submission Deadline** | *Proposals must be received by the Office of State Procurement Services by:***Submission Deadline:** November 1, 2024, no later than 11:59 p.m., local time.*Proposals must be submitted electronically to:* Proposals@maine.gov  |

TABLE OF CONTENTS

|  |  |
| --- | --- |
|  | **Page** |
|  |  |
| **PUBLIC NOTICE** | **3** |
|  |  |
| **RFP DEFINITIONS/ACRONYMS** | **4** |
|  |  |
| **PART I INTRODUCTION** | **5** |
| 1. PURPOSE AND BACKGROUND
 |  |
| 1. GENERAL PROVISIONS
 |  |
| 1. CONTRACT TERM
 |  |
| 1. NUMBER OF AWARDS
 |  |
|  |  |
| **PART II SCOPE OF SERVICES TO BE PROVIDED** | **8** |
|  |  |
| **PART III KEY RFP EVENTS** | **10** |
| 1. QUESTIONS
 |  |
| 1. AMENDMENTS
 |  |
| 1. SUBMITTING THE PROPOSAL
 |  |
|  |  |
| **PART IV PROPOSAL SUBMISSION REQUIREMENTS** | **12** |
|  |  |
| **PART V PROPOSAL EVALUATION AND SELECTION** | **14** |
| 1. EVALUATION PROCESS – GENERAL INFORMATION
 |  |
| 1. SCORING WEIGHTS AND PROCESS
 |  |
| 1. SELECTION AND AWARD
 |  |
| 1. APPEAL OF CONTRACT AWARDS
 |  |
|  |  |
| **PART VI CONTRACT ADMINISTRATION AND CONDITIONS** | **16** |
| 1. CONTRACT DOCUMENT
 |  |
| 1. STANDARD STATE CONTRACT PROVISIONS
 |  |
|  |  |
| **PART VII RFP APPENDICES AND RELATED DOCUMENTS** | **17** |
|  **APPENDIX A** – PROPOSAL COVER PAGE |  |
|  **APPENDIX B** – RESPONSIBLE BIDDER CERTIFICATION |  |
|  **APPENDIX C** – QUALIFICATIONS and EXPERIENCE FORM |  |
|  **APPENDIX D** – COST PROPOSAL FORM |  |
|  **APPENDIX E** – SUBMITTED QUESTIONS FORM  |  |
|  |  |
|  |  |
|  |  |

PUBLIC NOTICE

**\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\***

**State of Maine**

**Governor’s Office of Policy Innovation and the Future**

**RFP# 202409168**

**Climate Vulnerability Assessment of State Assets**

The State of Maine is seeking proposals for a climate vulnerability assessment of state assets. This project will include expanding the currently available information on the vulnerability of state assets to climate hazards, developing a framework for understanding and mitigating vulnerabilities, and developing strategies for state agencies to address asset vulnerabilities, in alignment with the State’s climate action plan.

A copy of the RFP, as well as the Question & Answer Summary and all amendments related to the RFP, can be obtained at: <https://www.maine.gov/dafs/bbm/procurementservices/vendors/rfps>

Proposals must be submitted to the State of Maine Office of State Procurement Services, via e-mail, at: Proposals@maine.gov. Proposal submissions must be received no later than 11:59 p.m., local time, on Friday, November 1, 2024. Proposals will be opened the following business day.

**\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\***

**RFP TERMS/ACRONYMS with DEFINITIONS**

The following terms and acronyms, as referenced in the RFP, shall have the meanings indicated below:

|  |  |
| --- | --- |
| **Term/Acronym** | **Definition** |
| **Department** | Governor’s Office of Policy Innovation and the Future |
| **FEMA** | Federal Emergency Management Agency  |
| **GOPIF** | Governor’s Office of Policy Innovation and the Future  |
| **Maine Won’t Wait** | Maine State Climate Action Plan |
| **MCC** | Maine Climate Council |
| **RFP** | Request for Proposal |
| **SHMP** | State Hazard Mitigation Plan |
| **State** | State of Maine |
| **State Asset** | Real property owned or leased by the State of Maine such as land, buildings, and infrastructure.  |
| **Vulnerability**  | Climate vulnerability. The combination of exposure, sensitivity, and adaptive capacity of a given asset to climate hazard impacts.  |

**State of Maine - Governor’s Office of Policy Innovation and the Future**

**RFP# 202409168**

**Climate Vulnerability Assessment of State Assets**

**PART I INTRODUCTION**

1. **Purpose and Background**

The Governor’s Office of Policy Innovation and the Future (GOPIF) is seeking proposals to perform a climate vulnerability assessment of state assets as defined in this Request for Proposal (RFP) document.

The objectives of this effort include:

1. Assessing the climate hazards and impacts to which state assets are exposed, and the consequences for public services of impairment or failure of the assets.
2. Developing recommendations tailored to state agencies and their missions for climate hazard mitigation and adaptation efforts for assets and operations.

This document provides instructions for submitting proposals, the procedure and criteria by which the awarded Bidder will be selected, and the contractual terms which will govern the relationship between the State of Maine (State) and the awarded Bidder.

In November 2019, Governor Mills issued an executive order directing the state government to “[Lead By Example](https://www.maine.gov/governor/mills/news/governor-mills-signs-executive-order-directing-state-government-lead-example-embracing-energy)” in investing in energy efficiency, renewable energy, and emissions reductions; promoting health and sustainability in the workplace; and building resilient infrastructure**.** One outcome of this project will be a set of recommendations to inform and assist state agencies in their efforts to reduce state asset vulnerabilities to climate impacts and build resilient infrastructure.

The state’s four-year climate action plan, [Maine Won’t Wait](https://www.maine.gov/climateplan/the-plan), recommends that the state “Assess Climate Vulnerability and Provide Climate-Ready Design Guidance”. Specifically, the plan recommends that the state complete a statewide infrastructure vulnerability assessment. The assessment is intended to provide an understanding of 1) the climate hazards to which infrastructure assets are exposed, the likelihood of that hazard occurring, and how the intensity and likelihood of those hazards may change over time; 2) the asset’s susceptibility to damage or failure given its location, design, age, condition, and state of repair; and 3) the consequences that impairment or failure of the asset will have on public safety and services.

A 2023 “Building Resilient Infrastructure and Communities” (BRIC) grant from the Federal Emergency Management Agency (FEMA) will support the Governor’s Office of Policy Innovation and the Future (GOPIF) to conduct this assessment. This effort seeks to expand and centralize information on the vulnerability of state assets. In 2023 the Maine Emergency Management Agency (MEMA) conducted the most recent FEMA-required [State Hazard Mitigation Plan](https://www.maine.gov/mema/sites/maine.gov.mema/files/inline-files/Maine_SHMP2023_Final_full.pdf) (SHMP), which serves as a foundational resource for understanding natural and climate hazards and impacts across the state. Developing an expanded assessment for state assets will help the state prepare for short- and long-term climate change resilience needs. Prioritizing pre-disaster risk reduction leads to increased resilient infrastructure in support of public safety, health, public services, and cost savings.

GOPIF invites responses from qualified firms to provide information on the following:

1. Their expertise in leading climate vulnerability assessments of infrastructure assets and system services.
2. Their expertise developing climate hazard mitigation and adaptation strategies, with emphasis on reducing risk to public services.
3. Familiarity with the latest research on climate change forecasts, projections, and time frames.
4. Familiarity with federal and state guidance on climate adaptation for public infrastructure.

The scope of work is expected to inform future projects including development of a siting and design tool emphasizing resiliency in public buildings. Bidders may include considerations of how this scope of work in this RFP might inform future efforts.

1. **General Provisions**
	1. From the time the RFP is issued until award notification is made, all contact with the State regarding the RFP must be made through the RFP Coordinator. No other person/ State employee is empowered to make binding statements regarding the RFP. Violation of this provision may lead to disqualification from the bidding process, at the State’s discretion.
	2. Issuance of the RFP does not commit the Department to issue an award or to pay expenses incurred by a Bidder in the preparation of a response to the RFP. This includes attendance at personal interviews or other meetings and software or system demonstrations, where applicable.
	3. All proposals must adhere to the instructions and format requirements outlined in the RFP and all written supplements and amendments (such as the Summary of Questions and Answers), issued by the Department. Proposals are to follow the format and respond to all questions and instructions specified below in the “Proposal Submission Requirements” section of the RFP.
	4. Bidders will take careful note that in evaluating a proposal submitted in response to the RFP, the Department will consider materials provided in the proposal, information obtained through interviews/presentations (if any), and internal Departmental information of previous contract history with the Bidder (if any). The Department also reserves the right to consider other reliable references and publicly available information in evaluating a Bidder’s experience and capabilities.
	5. The proposal must be signed by a person authorized to legally bind the Bidder and must contain a statement that the proposal and the pricing contained therein will remain valid and binding for a period of 180 days from the date and time of the bid opening.
	6. The RFP and the awarded Bidder’s proposal, including all appendices or attachments, will be the basis for the final contract, as determined by the Department.
	7. Following announcement of an award decision, all submissions in response to this RFP will be public records, available for public inspection pursuant to the State of Maine Freedom of Access Act (FOAA) ([1 M.R.S. § 401](http://www.mainelegislature.org/legis/statutes/1/title1sec401.html) et seq.).
	8. The Department, at its sole discretion, reserves the right to recognize and waive minor informalities and irregularities found in proposals received in response to the RFP.
	9. All applicable laws, whether or not herein contained, are included by this reference. It is the Bidder’s responsibility to determine the applicability and requirements of any such laws and to abide by them.
2. **Contract Term**

The Department is seeking a cost-efficient proposal to provide services, as defined in the RFP, for the anticipated contract period defined in the table below. Please note, the dates below are estimated and may be adjusted, as necessary, in order to comply with all procedural requirements associated with the RFP and the contracting process. The actual contract start date will be established by a completed and approved contract.

Contract Renewal: Following the initial term of the contract, the Department may opt to renew the contract for one (1) renewal periods, as shown in the table below, and subject to continued availability of funding and satisfactory performance.

The term of the anticipated contract, resulting from the RFP, is defined as follows:

|  |  |  |
| --- | --- | --- |
| **Period** | **Start Date** | **End Date** |
| Initial Period of Performance | 12/19/2024 | 11/30/2025 |
| Renewal Period #1 | 12/01/2025 | 11/30/2026 |

The Department reserves the right to modify the initial contract term at its sole discretion. If further analysis is needed in specific areas contained within this RFP, additional work could result.

1. **Number of Awards**

The Department anticipates making one (1) award as a result of the RFP process.

**PART II** **SCOPE OF SERVICES TO BE PROVIDED**

1. **Introduction**

The scope of work outlines the objectives and tasks related to this project. In developing and providing requested services, consideration should be given to the following objectives:

1. This assessment is intended to evaluate the vulnerability of state assets to climate impacts and provide agency-specific priorities and recommendations.
2. The assessment should consider physical risk to assets and subsequent consequences to the ability of agencies to carry out their missions.
3. The assessment of risk and consequences should inform the development of climate hazard mitigation and adaptation strategies to reduce vulnerabilities and increase resilience.
4. Types of assets for this investigation may include owned and leased real property (buildings, land, and infrastructure).

There are assets and areas of importance to addressing state asset vulnerabilities that are not owned by the state and therefore will not be included in the detailed analysis. For example, telecommunications, energy and electric grid infrastructure, and drinking water/stormwater/wastewater infrastructure may be related to the ability of state agencies to carry out their missions but are not state-owned assets. This assessment is not intended to evaluate the vulnerability of these facilities. However, secondary or cascading impacts to state operations resulting from the impairment or loss of services from these facilities may be included. Where relevant, assessing vulnerability of these assets and areas of importance can be noted as an area for future effort.

1. **Tasks**

**Task 1: Develop an inventory of state assets.**

GOPIF will coordinate engagement with participating state agency representatives to provide the selected Bidder with relevant state asset information.

1. Inventory detail should include (at a minimum): GPS and address location, building type, age, condition (state of repair), primary use, and related public services.
2. The selected Bidder will assist agencies to determine risk-tolerance and criticality for assets or asset types.

**Task 2: Develop climate impact scenarios for multiple hazards across the state.**
The outcome of this task will include projections for climate impact scenarios and their implications for the impacts of climate hazards on Maine state assets.

1. Identify a list of primary natural hazards and time horizons for the analysis (e.g., present day, 2030, and 2050), and where feasible identify a list of secondary hazards or cascading impacts.
2. The selected Bidder will assist agencies to understand climate hazards and asset exposures.

This task should be informed by:

* The 2023 [Maine State Hazard Mitigation Plan](https://www.maine.gov/mema/sites/maine.gov.mema/files/inline-files/Maine_SHMP2023_Final_full.pdf)
* The 2024 [Maine Climate Council Scientific and Technical Subcommittee Report](https://www.maine.gov/future/sites/maine.gov.future/files/inline-files/STS_2024_digital.pdf)

**Task 3: Conduct a screening-level assessment of vulnerability and impact for each asset or asset type**.
Given the climate impact scenarios produced in Task 2, the outcome of this task will include a combination of quantitative and qualitative analyses of climate hazard impacts to assets and interruptions to public services.

1. The outcomes of the assessment should include
	1. a relative vulnerability score (either quantitative or qualitative)
	2. an impact or consequence assessment
	3. an evaluation of potential adaptive capacity
	4. equity implications for public service interruptions
2. The selected Bidder will assist agencies to understand and assess the impacts of impairment of an asset or facility.

**Task 4: Recommend climate hazard mitigation and adaptation options for the State and individual agencies.**

This effort involves the development and prioritization of strategies and actions that reduce risk and close resilience gaps for physical assets as well as the ability of agencies to carry out their missions and deliver services.

1. Recommendations should cover
	1. Short-, medium-, and long-term actions and relative cost considerations.
	2. Whole of government actions for integrating and coordinating resilience efforts.
	3. Outcome metrics for tracking progress and resiliency improvements across state agencies.
2. The selected Bidder will assist and collaborate with agencies to develop mitigation and adaptation strategies.

**PART III KEY RFP EVENTS**

1. **Questions**
	1. **General Instructions:** It is the responsibility of all Bidders and other interested parties to examine the entire RFP and to seek clarification, in writing, if they do not understand any information or instructions.
		1. Bidders and other interested parties should use **Appendix E** (Submitted Questions Form) for submission of questions. The form is to be submitted as a WORD document.
		2. The Submitted Questions Form must be submitted, by e-mail, and received by the RFP Coordinator identified on the cover page of the RFP as soon as possible but no later than the date and time specified on the RFP cover page.
		3. Submitted Questions must include the RFP Number and Title in the subject line of the e-mail. The Department assumes no liability for assuring accurate/complete/on time e-mail transmission and receipt.
	2. **Question & Answer Summary:** Responses to all questions will be compiled in writing and posted on the following website no later than seven (7) calendar days prior to the proposal due date: [Office of State Procurement Services RFP Page](https://www.maine.gov/dafs/bbm/procurementservices/vendors/rfps). It is the responsibility of all interested parties to go to this website to obtain a copy of the Question & Answer Summary. Only those answers issued in writing on this website will be considered binding.
2. **Amendments**

All amendments released in regard to the RFP will also be posted on the following website: [Office of State Procurement Services RFP Page](https://www.maine.gov/dafs/bbm/procurementservices/vendors/rfps). It is the responsibility of all interested parties to go to this website to obtain amendments. Only those amendments posted on this website are considered binding.

1. **Submitting the Proposal**
	1. **Proposals Due:** Proposals must be received no later than 11:59 p.m. local time, on the date listed on the cover page of the RFP.
		1. Any e-mails containing original proposal submissions or any additional or revised proposal files, received after the 11:59 p.m. deadline, will be rejected without exception.
	2. **Delivery Instructions:** E-mail proposal submissions are to be submitted to the State of Maine Office of State Procurement Services at Proposals@maine.gov.
		1. Only proposal submissions received by e-mail will be considered. The Department assumes no liability for assuring accurate/complete e-mail transmission and receipt.
			1. Proposal submission e-mails that are successfully received by the proposals@maine.gov inbox will receive an automatic reply stating as such.
		2. E-mails containing links to file sharing sites or online file repositories will not be accepted as submissions. Only e-mail proposal submissions that have the actual requested files attached will be accepted.
		3. Encrypted e-mails received which require opening attachments and logging into a proprietary system will not be accepted as submissions. Please check with your organization’s Information Technology team to ensure that your security settings will not encrypt your proposal submission.
		4. File size limits are 25MB per e-mail. Bidders may submit files separately across multiple e-mails, as necessary, due to file size concerns. All e-mails and files must be received by the due date and time listed above.
		5. Bidders are to insert the following into the subject line of their e-mail proposal submission: **“RFP# 202409168 Proposal Submission – [Bidder’s Name]”**
		6. Bidder’s proposal submissions are to be broken down into multiple files, with each file named as it is titled in bold below, and include:
* **File 1 [Bidder’s Name] – Preliminary Information:**

*PDF format preferred*

**Appendix A** (Proposal Cover Page)

**Appendix B** (Responsible Bidder Certification)

All required eligibility documentation stated in PART IV, Section I.

* **File 2 [Bidder’s Name] – Organization Qualifications and Experience:**

*PDF format preferred*

**Appendix C** (Organization Qualifications and Experience Form) and all required information and attachments stated in PART IV, Section II.

* **File 3 [Bidder’s Name] – Proposed Services:**

*PDF format preferred*

All required information and attachments stated in PART IV, Section III.

* **File 4 [Bidder’s Name] – Cost Proposal:**

*PDF format preferred*

**Appendix D** (Cost Proposal Form) and all required information and attachments stated in PART IV, Section IV.

**PART IV PROPOSAL SUBMISSION REQUIREMENTS**

This section contains instructions for Bidders to use in preparing their proposals. The Department seeks detailed yet succinct responses that demonstrate the Bidder’s qualifications, experience, and ability to perform the requirements specified throughout the RFP.

The Bidder’s proposal must follow the outline used below, including the numbering, section, and sub-section headings. Failure to use the outline specified in PART IV, or failure to respond to all questions and instructions throughout the RFP, may result in the proposal being disqualified as non-responsive or receiving a reduced score. The Department, and its evaluation team, has sole discretion to determine whether a variance from the RFP specifications will result either in disqualification or reduction in scoring of a proposal. Rephrasing of the content provided in the RFP will, at best, be considered minimally responsive.

Bidders are not to provide additional attachments beyond those specified in the RFP for the purpose of extending their response. Additional materials not requested will not be considered part of the proposal and will not be evaluated. Include any forms provided in the submission package or reproduce those forms as closely as possible. All information must be presented in the same order and format as described in the RFP.

**Proposal Format and Contents**

**Section I Preliminary Information** (File #1)

* 1. **Proposal Cover Page**

Bidders must complete **Appendix A** (Proposal Cover Page). It is critical that the cover page show the specific information requested, including Bidder address(es) and other details listed. The Proposal Cover Page must be dated and signed by a person authorized to enter into contracts on behalf of the Bidder.

* 1. **Responsible Bidder Certification**

Bidders must complete **Appendix B** (Responsible Bidder Certification). The Responsible Bidder Certification must be dated and signed by a person authorized to enter into contracts on behalf of the Bidder.

**Section II Organization Qualifications and Experience** (File #2)

* 1. **Overview of the Organization**

Bidders must complete **Appendix C** (Qualifications and Experience Form) describing their qualifications and skills to provide the requested services in the RFP. Bidders must include three examples of projects which demonstrate their experience and expertise in performing these services as well as highlighting the Bidder’s stated qualifications and skills.

* 1. **Subcontractors**

If subcontractors are to be used, Bidders must provide a list that specifies the name, address, phone number, contact person, and a brief description of the subcontractors’ organizational capacity and qualifications.

* 1. **Organizational Chart**

Bidders must provide an organizational chart.  The organizational chart must include the project being proposed.  Each position must be identified by position title and corresponding to the personnel job descriptions.

* 1. **Litigation**

Bidders must attach a list of all current litigation in which the Bidder is named and a list of all closed cases that have closed within the past five (5) years in which the Bidder paid the claimant either as part of a settlement or by decree.  For each, list the entity bringing suit, the complaint, the accusation, amount, and outcome.

* 1. **Certificate of Insurance**

Bidders must provide a certificate of insurance on a standard ACORD form (or the equivalent) evidencing the Bidder’s general liability, professional liability and any other relevant liability insurance policies that might be associated with the proposed services.

**Section III Proposed Services** (File #3)

* 1. **Services to be Provided**

Discuss the Scope of Services referenced above in Part II of the RFP and what the Bidder will offer. Give particular attention to describing the methods and resources you will use and how you will accomplish the tasks involved. Also, describe how you will ensure expectations and/or desired outcomes as a result of these services will be achieved. If subcontractors are involved, clearly identify the work each will perform.

* 1. **Implementation - Work Plan**

Provide a realistic work plan for the implementation of the program through the first contract period. Display the work plan in a timeline chart. Concisely describe each program development and implementation task, the month it will be carried out and the person or position responsible for each task. If applicable, make note of all tasks to be delegated to subcontractors.

**Section IV Cost Proposal** (File #4)

* 1. **General Instructions**
		1. Bidders must submit a cost proposal that covers the period starting 12/19/2024 and ending on 11/30/2025.
		2. The cost proposal must include the costs necessary for the Bidder to fully comply with the contract terms, conditions, and RFP requirements.
		3. No costs related to the preparation of the proposal for the RFP, or to the negotiation of the contract with the Department, may be included in the proposal. Only costs to be incurred after the contract effective date that are specifically related to the implementation or operation of contracted services may be included.
	2. **Cost Proposal Form Instructions**

Bidders must fill out **Appendix D** (Cost Proposal Form), following the instructions detailed here and in the form. Failure to provide the requested information, and to follow the required cost proposal format provided, may result in the exclusion of the proposal from consideration, at the discretion of the Department.

**PART V PROPOSAL EVALUATION AND SELECTION**

Evaluation of the submitted proposals will be accomplished as follows:

1. **Evaluation Process – General Information**
	1. An evaluation team, composed of qualified reviewers, will judge the merits of the proposals received in accordance with the criteria defined in the RFP.
	2. Officials responsible for making decisions on the award selection will ensure that the selection process accords equal opportunity and appropriate consideration to all who are capable of meeting the specifications. The goals of the evaluation process are to ensure fairness and objectivity in review of the proposals and to ensure that the contract is awarded to the Bidder whose proposal provides the best value to the State of Maine.
	3. The Department reserves the right to communicate and/or schedule interviews/presentations with Bidders, if needed, to obtain clarification of information contained in the proposals received. The Department may revise the scores assigned in the initial evaluation to reflect those communications and/or interviews/presentations. Changes to proposals, including updating or adding information, will not be permitted during any interview/presentation process and, therefore, Bidders must submit proposals that present their rates and other requested information as clearly and completely as possible.
2. **Scoring Weights and Process**
	1. **Scoring Weights:** The score will be based on a 100-point scale and will measure the degree to which each proposal meets the following criteria.

**Section I.**  **Preliminary Information (No Points)**

 Includes all elements addressed above in Part IV, Section I.

**Section II. Organization Qualifications and Experience (30 points)**

Includes all elements addressed above in Part IV, Section II.

**Section III. Proposed Services (45 points)**

Includes all elements addressed above in Part IV, Section III.

**Section IV. Cost Proposal (25 points)**

Includes all elements addressed above in Part IV, Section IV.

* 1. **Scoring Process:** For proposals that demonstrate meeting the eligibility requirements in Section I, the evaluation team will use a consensus approach to evaluate and score Sections II & III above. Members of the evaluation team will not score those sections individually but, instead, will arrive at a consensus as to assignment of points for each of those sections. Sections IV, the Cost Proposal, will be scored as described below.
	2. **Scoring the Cost Proposal:** The total cost proposed for conducting all the functions specified in the RFP will be assigned a score according to a mathematical formula. The lowest bid will be awarded 25 points. Proposals with higher bids values will be awarded proportionately fewer points calculated in comparison with the lowest bid.

The scoring formula is:

(Lowest submitted cost proposal / Cost of proposal being scored) x (25) = pro-rated score

No Best and Final Offers: The State of Maine will not seek or accept a best and final offer (BAFO) from any Bidder in this procurement process.  All Bidders are expected to provide their best value pricing with the submission of their proposal.

* 1. **Negotiations:** The Department reserves the right to negotiate with the awarded Bidder to finalize a contract. Such negotiations may not significantly vary the content, nature or requirements of the proposal or the Department’s Request for Proposal to an extent that may affect the price of goods or services requested. The Department reserves the right to terminate contract negotiations with an awarded Bidder who submits a proposed contract significantly different from the proposal they submitted in response to the advertised RFP. In the event that an acceptable contract cannot be negotiated with the highest ranked Bidder, the Department may withdraw its award and negotiate with the next-highest ranked Bidder, and so on, until an acceptable contract has been finalized. Alternatively, the Department may cancel the RFP, at its sole discretion.
1. **Selection and Award**
	1. The final decision regarding the award of the contract will be made by representatives of the Department subject to approval by the State Procurement Review Committee.
	2. Notification of conditional award selection or non-selection will be made in writing by the Department.
	3. Issuance of the RFP in no way constitutes a commitment by the State of Maine to award a contract, to pay costs incurred in the preparation of a response to the RFP, or to pay costs incurred in procuring or contracting for services, supplies, physical space, personnel or any other costs incurred by the Bidder.
	4. The Department reserves the right to reject any and all proposals or to make multiple awards.
2. **Appeal of Contract Awards**

Any person aggrieved by the award decision that results from the RFP may appeal the decision to the Director of the Bureau of General Services in the manner prescribed in [5 M.R.S.A. § 1825-E](http://www.mainelegislature.org/legis/statutes/5/title5sec1825-E.html) and [18-554 Code of Maine Rules Chapter 120](https://www.maine.gov/dafs/bbm/procurementservices/policies-procedures/chapter-120).  The appeal must be in writing and filed with the Director of the Bureau of General Services, 9 State House Station, Augusta, Maine, 04333-0009 within 15 calendar days of receipt of notification of conditional contract award.

**PART VI CONTRACT ADMINISTRATION AND CONDITIONS**

1. **Contract Document**
	1. The awarded Bidder will be required to execute a State of Maine Service Contract with appropriate riders as determined by the issuing department.

The complete set of standard State of Maine Service Contract documents, along with other forms and contract documents commonly used by the State, may be found on the Office of State Procurement Services’ website at the following link: [Office of State Procurement Services Forms Page](https://www.maine.gov/dafs/bbm/procurementservices/forms)

* 1. Allocation of funds is final upon successful negotiation and execution of the contract, subject to the review and approval of the State Procurement Review Committee. Contracts are not considered fully executed and valid until approved by the State Procurement Review Committee and funds are encumbered. No contract will be approved based on an RFP which has an effective date less than fourteen (14) calendar days after award notification to Bidders. (Referenced in the regulations of the Department of Administrative and Financial Services, [Chapter 110, § 3(B)(i)](https://www.maine.gov/dafs/bbm/procurementservices/policies-procedures/chapter-110).)

This provision means that a contract cannot be effective until at least 14 calendar days after award notification.

* 1. The State recognizes that the actual contract effective date depends upon completion of the RFP process, date of formal award notification, length of contract negotiation, and preparation and approval by the State Procurement Review Committee. Any appeals to the Department’s award decision(s) may further postpone the actual contract effective date, depending upon the outcome. The contract effective date listed in the RFP may need to be adjusted, if necessary, to comply with mandated requirements.
	2. In providing services and performing under the contract, the awarded Bidder must act as an independent contractor and not as an agent of the State of Maine.
1. **Standard State Contract Provisions**
	1. Contract Administration

Following the award, a Contract Administrator from the Department will be appointed to assist with the development and administration of the contract and to act as administrator during the entire contract period. Department staff will be available after the award to consult with the awarded Bidder in the finalization of the contract.

* 1. Payments and Other Provisions

The State anticipates paying the Contractor on the basis of net 30 payment terms, upon the receipt of an accurate and acceptable invoice. An invoice will be considered accurate and acceptable if it contains a reference to the State of Maine contract number, contains correct pricing information relative to the contract, and provides any required supporting documents, as applicable, and any other specific and agreed-upon requirements listed within the contract that results from the RFP.

**PART VII LIST OF RFP APPENDICES AND RELATED DOCUMENTS**

**Appendix A** – Proposal Cover Page

**Appendix B** – Responsible Bidder Certification

**Appendix C** – Qualifications and Experience Form

**Appendix D** – Cost Proposal Form

**Appendix E** – Submitted Question Form

**APPENDIX A**

**State of Maine**

**Governor’s Office of Policy Innovation and the Future**

**PROPOSAL COVER PAGE**

**RFP# 202409168**

**Climate Vulnerability Assessment of State Assets**

|  |  |
| --- | --- |
| **Bidder’s Organization Name:** |  |
| **Chief Executive - Name/Title:** |  |
| **Tel:** |  | **E-mail:** |  |
| **Headquarters Street Address:** |  |
| **Headquarters City/State/Zip:** |  |
| ***(Provide information requested below if different from above)*** |
| **Lead Point of Contact for Proposal - Name/Title:** |  |
| **Tel:** |  | **E-mail:** |  |
| **Headquarters Street Address:** |  |
| **Headquarters City/State/Zip:** |  |

* This proposal and the pricing structure contained herein will remain firm for a period of 180 days from the date and time of the bid opening.
* No personnel currently employed by the Department or any other State agency participated, either directly or indirectly, in any activities relating to the preparation of the Bidder’s proposal.
* No attempt has been made, or will be made, by the Bidder to induce any other person or firm to submit or not to submit a proposal.
* The above-named organization is the legal entity entering into the resulting contract with the Department if they are awarded the contract.
* The undersigned is authorized to enter contractual obligations on behalf of the above-named organization.

*To the best of my knowledge, all information provided in the enclosed proposal, both programmatic and financial, is complete and accurate at the time of submission.*

|  |  |
| --- | --- |
| **Name (Print):** | **Title:** |
| **Authorized Signature:** | **Date:** |

**APPENDIX B**

**State of Maine**

**Governor’s Office of Policy Innovation and the Future**

**RESPONSIBLE BIDDER CERTIFICATION**

**RFP# 202409168**

**Climate Vulnerability Assessment of State Assets**

|  |  |
| --- | --- |
| **Bidder’s Organization Name:** |  |

*By signing this document, I certify to the best of my knowledge and belief that the aforementioned organization, its principals and any subcontractors named in this proposal:*

1. *Are not presently debarred, suspended, proposed for debarment, and declared ineligible or voluntarily excluded from bidding or working on contracts issued by any governmental agency.*
2. *Have not within three years of submitting the proposal for this contract been convicted of or had a civil judgment rendered against them for:*
	1. *Fraud or a criminal offense in connection with obtaining, attempting to obtain, or performing a federal, state, or local government transaction or contract.*
	2. *Violating Federal or State antitrust statutes or committing embezzlement, theft, forgery, bribery, falsification or destruction of records, making false statements, or receiving stolen property.*
3. *Are not presently indicted for or otherwise criminally or civilly charged by a governmental entity (Federal, State or Local) with commission of any of the offenses enumerated in paragraph (b) of this certification.*
4. *Have not within a three (3) year period preceding this proposal had one or more federal, state, or local government transactions terminated for cause or default*.
5. *Have not entered into a prior understanding, agreement, or connection with any corporation, firm, or person submitting a response for the same materials, supplies, equipment, or services and this proposal is in all respects fair and without collusion or fraud. The above-mentioned entities understand and agree that collusive bidding is a violation of state and federal law and can result in fines, prison sentences, and civil damage awards.*
6. *Is not a foreign adversary business entity (*[*https://www.maine.gov/oit/prohibited-technologies*](https://www.maine.gov/oit/prohibited-technologies)*).*
7. *Is not on the list of prohibited companies (*[*https://www.maine.gov/oit/prohibited-technologies*](https://www.maine.gov/oit/prohibited-technologies)*) or does not obtain or purchase any information or communications technology or services included on the list of prohibited information and communications technology and services* [*https://www.maine.gov/oit/prohibited-technologies*](https://www.maine.gov/oit/prohibited-technologies) *(Title 5 §2030-B).*

|  |  |
| --- | --- |
| **Name (Print):** | **Title:** |
| **Authorized Signature:** | **Date:** |

**APPENDIX C**

**State of Maine**

**Governor’s Office of Policy Innovation and the Future**

## QUALIFICATIONS and EXPERIENCE FORM

**RFP# 202409168**

**Climate Vulnerability Assessment of State Assets**

|  |  |
| --- | --- |
| **Bidder’s Organization Name:** |  |

|  |
| --- |
| **Present a brief statement of qualifications. Describe the history of the Bidder’s organization, especially regarding skills pertinent to the specific work required by the RFP and any special or unique characteristics of the organization which would make it especially qualified to perform the required work activities. You may expand this form and use additional pages to provide this information.** |
|  |

|  |
| --- |
| **Provide a description of projects that occurred within the past five years which reflect experience and expertise needed in performing the functions described in Part II – Scope of Services to be Provided of the RFP. Please note that contract history with the State of Maine, whether positive or negative, may be considered in rating proposals even if not provided by the Bidder.** |

|  |
| --- |
| **Project One** |
| **Client Name:** |  |
| **Client Contact Person:** |  |
| **Telephone:** |  |
| **E-Mail:** |  |
| **Brief Description of Project** |
|  |

|  |
| --- |
| **Project Two** |
| **Client Name:** |  |
| **Client Contact Person:** |  |
| **Telephone:** |  |
| **E-Mail:** |  |
| **Brief Description of Project** |
|  |

|  |
| --- |
| **Project Three** |
| **Client Name:** |  |
| **Client Contact Person:** |  |
| **Telephone:** |  |
| **E-Mail:** |  |
| **Brief Description of Project** |
|  |

**APPENDIX D**

**State of Maine**

**Governor’s Office of Policy Innovation and the Future**

**COST PROPOSAL FORM**

**RFP# 202409168**

**Climate Vulnerability Assessment of State Assets**

**Instructions:** Bidders must complete the table below. The details and deliverables associated with each Task are outlined in Part II of the RFP and must be included in the Total Cost for All Tasks.

The Total Cost for All Tasks will be used in the scoring formula for the cost proposal as defined in Part V, B, 3 of the RFP.

|  |  |
| --- | --- |
| **Bidder’s Organization Name:** |  |
| **Total Cost for All Tasks:** | **$** |

 **APPENDIX E**

**State of Maine**

**Governor’s Office of Policy Innovation and the Future
SUBMITTED QUESTIONS FORM**

**RFP# 202409168**

**Climate Vulnerability Assessment of State Assets**

This form should be used by Bidders when submitting written questions to the RFP Coordinator as defined in Part III of the RFP.

If a question is not related to any section of the RFP, enter “N/A” under the RFP Section & Page Number. Add additional rows as necessary.

|  |  |
| --- | --- |
| **Organization Name:** |  |

|  |  |
| --- | --- |
| **RFP Section & Page Number** | **Question** |
|  |  |
|  |  |
|  |  |
|  |  |
|  |  |
|  |  |
|  |  |
|  |  |
|  |  |
|  |  |
|  |  |
|  |  |
|  |  |
|  |  |
|  |  |
|  |  |