## Instructions
Developing Your Calendar Year 2025 Workplan
• Workplans should reflect those activities that:
1. Consider local conditions (resources, assets, barriers, etc. See Community Capacity Self-Assessment results and Maine Tracking Network data)
2. Are consistent with the contract deliverables described in the LPPF contract (see Contract Deliverables tab).
3. Consider community-level feedback collected through coalition meetings and individual meetings with partners.
4. Are most likely to achieve the greatest impact on lead poisoning prevention, through reducing the number of children with elevated blood lead levels and creating safer housing (Refer to Example Logic Model).
Entering Your Workplan
• Use the Workplan Reporting tab in this workbook to enter your workplan. The EXAMPLE Workplan Reporting sheet is provided to help you.
• Populate the Workplan Reporting tab header with your organizational information, service area and LPPF grant single point of contact.
• Populate columns B-G in the Workplan Reporting tab. Note:The example workplan's colors connect activities to the corresponding contract deliverable. Community Partner (CP) proposed workplans may use color if helpful, but it is not required.
B: Deliverable Category: This refers to the Rider A deliverable. Please enter the deliverable in each row, or merge and center the deliverable across all the activity rows pertaining to that deliverable.
C: Detailed Activity: Activities are your step-by-step actions to meet the contract deliverables. Please be specific. Articulate each activity in a separate row. Add additional rows as needed.
D: Intended Outputs: These are the short-term measurable product of your activities, such as # trainings completed; # policy ideas reviewed, etc.
E: Intended Outcomes: The anticipated short-term or intermediates changes achieved by your activities and their intended outputs. These outcomes do not need to be measured, but should show the progression of your activities to support the long term outcomes (fewer children with EBLLs and safer housing)
F: Timeline: The quarter and year the activity will be completed in.
G:Staff Responsible: The staff who will complete the activity. May include others within your organization or trusted partners as long as you can report on their outcomes.
Refer to the Example Logic Model for generic lead poisoning prevention activities, outputs, and outcomes to help you. Tailor your outputs and outcomes to your proposed activities and add specificity.
• Populate your working Housing Quality Improvement Policy/Systems Change goal in the last row of the Housing Quality Improvement Policy/Systems section of the workplan. This is long-term ambitious goal you hope to achieve that impacts the local housing and lead poisoning prevention system.
You may use the goal articulated in your RFP proposal or propose a new goal. Your Housing Quality Improvement Policy/Systems Change activities should build toward this long-term goal.
Submitting Your Workplan
• Email the entire Workplan and Quarterly Reporting excel workbook to Erin G. and Erin A.
• CLPPP staff will review and request a virtual meeting to discuss and revise your workplan, as needed. CLPPP must approve your workplan.
• Workplans can be revised during the contract year. CLPPP will require approval before moving forward with a new workplan. Contact Erin G. and Erin A. for more details.
Reporting Your Quarterly Progress
• Starting in CY 2025, report completed activities on the 2 GREEN tabs
| Enter your progress on the Workplan Reporting tab to the right of the approved 2025 Workplan. Populate columns H-X: |  | Contract Qtr | Months
| Complete the Status Update column each quarter to identify if the activity is in the planning phase, in process, completed or not started. |  | 1 | Jan-Mar
| Complete other columns according to the reporting quarter. |  | 2 | Apr-June
|  | Successes: briefly describe any positive results from your activities in the quarter. | 3 | July-Sept
|  | Challenges: briefly describe any barriers from your activities in the quarter. | 4 | Oct-Dec
Outputs: enter specific results from your activities with units, such as 8 landlords educated; 400 parents reached on Instagram/other social media reach, etc.
Assistance Requested from CLPPP: describe what CLPPP assistance could move your project forward. CLPPP may not have an immediate answer or resource but may be able to help you identify one.
• If an activity is marked as complete, you don't need to provide a status update in future quarters.
Enter any education and outreach activities completed in the Education and Outreach Detail tab. (Social media outreach does not need to be reported here).
The purpose of this tab is to capture specifics: who you have educated; what messages you provided; what tools you used. This information is used by CLPPP to understand what training and materials you need, and is provided to MaineHousing as match to their lead hazard control funding.
Please enter your education and outreach in both the workplan reporting and the education and outreach detail tabs. The entry in the workplan reporting should demonstrate how your education/outreach supports your larger deliverables and community goals; the Education and Outreach detail section is used to report on specifics.
Each education/outreach event should be listed in a separate row.
Type of Education/Outreach: Examples include: Health fair, One-on-one education; Training/Presentation; Display materials provided. You may list others if you describe them in detail.
Name of Education/Outreach Effort: The name of an event or description of displayed materials
Description of Audience: Provide an explanation of the audience with as much detail as is reasonable. See examples.
Primary Messages Provided: List the major take-home messages you provided. See examples.
# Reached / Trained: Count the number of people you estimate were engaged with the material provided. Please count those who read materials or engage with staff.
Do not count total attendees at community-wide event unless there was a reasonable chance they all saw, read or heard the messages provided. If you aren't sure of a number engaged, write unknown and describe your best guess in the notes field.
For materials left at a display or given to a partner to hand out, list # engaged as unknown and list the number of materials provided in the notes.
Materials Used: List the tipsheets or resources provided.
Tips and Tricks
• To insert a bullet either: A. Copy the bullet at left and paste into a cell. Or B: Select a blank cell, and then on the Insert tab, click Symbol. At the bottom of the dialog box, type 2022 in the Character code box. Then click Insert, and Close.
• To insert a hard return within a cell, type ALT+ENTER
• During quarterly reporting, if you want you see your Activities column next to your Status Update column you can "freeze" the activities column so it remains in place and you can easily scroll through right-ward columns. To do so, select the column to the right of the column you want to freeze.
Then select View, Freeze Panes and Freeze Panes again. You can now use the scroll arrows and bar on the lower right to move your data entry cells while keeping your workplan activities in place.
• During quarterly reporting in Q2-4 you can hide columns for previous quarters to focus on the reporting quarter at hand. Select the columns to hide, then right click and select Hide. You can undue this by highlighting the columns adjacent to those hidden and then right clicking and selecting Unhide.
Decision to exclude total attendees but clearly label how we are defining engaging.

## Workplan Reporting
Org name
Service Area
Reporting Dates
Date Submitted
Single Point of Contact
Date workplan last updated
WORKPLAN | [6 empty] | Status update | Q1 2025 |  |  |  | Q2 2025 |  |  |  | Q3 2025 |  |  |  | Q4 2025
Line | Deliverable Category | Detailed Activity | Intended Outputs | Intended Outcomes | Timeline | Staff Responsible | Current Status (planning, in progress, complete, not started) | Successes | Challenges | Outputs (with units) | Assistance Requested from CLPPP | Successes | Challenges | Outputs and units | Assistance Requested from CLPPP | Successes | Challenges | Outputs and units | Assistance Requested from CLPPP | Successes | Challenges | Outputs and units | Assistance Requested from CLPPP
1 | Community Capacity Self-Assessment
2
3 | Coalition Engagement
4
5
6
7 | Family Education
8
9
10
11
12 | Housing Quality Improvement Policy and Systems Change
13
14
15
16
17
18
19
GOAL | Housing Quality Improvement Policy and Systems Change Goal:
20 | Property Owner Education
21
22
23
24 | Facilitated Lead Dust Testing
25
26
27 | Partner with Primary Care Providers re: Screening
28
29
30
31
32 | Seeking Funding
33
34 | Participate in local housing collaboratives
35
36
37

## Education and Outreach Detail
| Quarter | Calendar Year | Date of Education/Outreach | Type of Education/Outreach | Name of Education/Outreach Effort | Description of Audience | Primary Messages Provided | # Reached / Trained | Materials Used | Notes
Example | 1 | 2025 | 1/1/25-3/31/25 | One-on-One | PH Nursing Visit | Families with low income receiving public health nursing services in Portland | Availability of free lead dust test kits | 22 | Baby Joe brochure
Example | 2 | 2025 | 4/22/25 | Community Event | Earth Day parade | City-wide audience in Saco/Biddeford, many young families | What is lead; Importance of blood lead testing | 23 | Tipsheet #1 and 3
Example | 3 | 2025 | 8/22/25 | Training | Landlord Association training on Essential Maintenance Practices | Property owners in Biddeford | How to use a free lead dust test kit; low cost ways to address chipping and peeling paint | 4 | Tipsheet #7, Get the Lead Out: Take Advantage of Unit Turnover | DEP assisted with the presentation
Example | 4 | 2025 | 11/3/25 | Display | Pediatric practice educational materials display | Parents of young children in Lewiston | Importance of blood lead testing | Unknown | Tipsheet #1 | 100 copies of tipsheet 1 provided. Cannot measure # reached.

## EXAMPLE Workplan Reporting
Org name
Service Area
Reporting Dates
Date Submitted
Single Point of Contact
Date workplan last updated
EXAMPLE WORKPLAN | [6 empty] | Status update | Q1 2025 |  |  |  | Q2 2025 |  |  |  | Q3 2025 |  |  |  | Q4 2025
Line | Deliverable Category | Detailed Activity | Intended Outputs | Intended Outcomes | Timeline | Staff Responsible | Current Status (planning, in progress, complete, not started) | Successess | Challenges | Outputs (with units) | Assistance Requested from CLPPP | Successess | Challenges | Outputs and units | Assistance Requested from CLPPP | Successess | Challenges | Outputs and units | Assistance Requested from CLPPP | Successess | Challenges | Outputs and units | Assistance Requested from CLPPP
1 | Community Capacity Self-Assessment | Re-visit 2024 community capacity self-assessment, as needed | Discussion completed among CP staff | Increased identification of new opportunities for capacity improvement; Increased community capacity for lead poisoning prevention | Q3 2025 | Karyn Butts | Not Started
2 | Coalition Engagement | Convene coalition and review approved workplan. | 1 coalition discussion complete; 10 members engaged; 2 coalition members identified who are willing to assist with implementation. | Increased strength and diversity of partnerships; Increased community capacity for lead poisoning prevention activities | Q1 2025 | Erin Arneson | Complete | Identified potential partner in local Head Start. Identified code enforcement contact for further discussion of potential systematic identified of chipping and peelng paint. | Contractors continue to be in short supply for lead abatement projects. | 10 attendees | Are there examples of promising practices for attracting more abatement contractors to the field?
3 |  | Present local Lead Poisoning Data and our LPPF workplan to municipal housing committee | 1 presentation complete; 20 attendees engaged | Increased community partner knowledge of childhood lead poisoning data, risk factors, and best practices; Increased areas of potential collaboration identified; Strengthened local partnerships | Q1 2025 | Karyn Butts | Complete | Made connections with two new partners. Identified opportunity to collaborate with partners to provide content to healthy housing status report for City. |  | 20 attendees
4 |  | Re-convene coalition to discuss workplan progress and barriers; review potential policy/systems changes | 1 coalition discussion complete; 10 members engaged | Increased consensus on policy/system changes needed; identified assets and barriers to policy/system change ideas presented | Q3 2025 | Karyn Butts | Planning
5 |  | If funds secured, partner with municipal housing committee to plan local safe housing summit | 1 committee convened | Increased strength and diversity of partnerships; Increased community capacity for lead poisoning prevention activities | Q4 2025 | Karyn Butts and Erin Arneson | Planning
6 | Family Education | Conduct mass media campaign | 1 campaign implemented; 300 Facebook users age 25-45 reached; 400 Instagram users age 30-44 reached; circulation in local newspaper | Increased family knowledge of lead dust as most common cause of lead poisoning | Q1 2025 | Erin Arneson | Complete | Achieved better reach than expected. Posts were shared by local healthcare practice | Had trouble assessing specific age of audience reached | •2000 facebook views and 2 shares • 1/4 pg ad placement in local newspaper; circulation of 8,900 • 1500 instagram views | Could you help us better target social media campaigns through boosted posts? Do you have any fresh campaign materials for Lead Poisoning Prevention Week in October?
7 |  | Complete presentations to local families on free lead dust test kits; offer to facilitate lead dust test kits for families | 4 presentations completed among family-serving organizations | Increased family knowledge of lead dust as most common cause of lead poisoning; Increased number of families engaged for receiving facilitation assistance on lead dust test kit | Q2 2025 | Erin Arneson | In Progress | Presented to Head Start's parent committee. They suggested offering free lead dust kits and facilitation service at their Family Fun day in May. | WIC office has little capacity to host a presentation until December 2025.
8 |  | Collaborate with local housing navigator to provide cleaning up lead dust information to newly housed families with young children; create plan for providing cleaning buckets | 1 plan created for providing information on cleaning up lead dust to families; 45 families reached per year with education materials; 10 families reached each year with cleaning buckets | Increased family knowledge of lead dust as most common cause of lead poisoning; Increased number of families educated on cleaning as prevention measure | Q2-Q3 2025 | Erin Arneson | Planning |  |  |  | How does MaineHousing's Housing Navigator funding work? Could we get a presentation from MaineHousing?
9 |  | Provide lead educational materials to social service organizations for distribution in their welcome packets | Materials provided to 4 social service organizations | Increased family knowledge of causes of lead poisoning; Increased awareness of importance of a blood lead test | Q3 2025 | Erin Arneson | Planning
10 |  | Re-run Feb mass media campaign to coincide with Lead Poisoning Prevention Week | 1 campaign implemented; 300 Facebook users age 25-45 reached; 400 Instagram users age 30-44 reached; circulation in local newspaper | Increased family knowledge of lead dust as most common cause of lead poisoning | Q4 2025 | Erin Arneson | Planning
11 | Housing Quality Improvement Policy and Systems Change | Convene coalition and present best practices housing quality improvement initiatives | 1 presentation created; 12 attendees engaged | Increased engagement with coalition; Increased consensus on policy/system changes needed | Q1 2025 | Karyn Butts and Erin Arneson | Complete | Presented three ideas for housing quality improvement. Coalition gravitated toward asking city to require proof of RRP certification when requesting a construction permit. Coalition had lots of questions about how to motivate home owners to request RRP certified contractors.
12 |  | Research coalition questions | 1 policy/system change idea list refined | Increased staff knowledge about potential policy/system changes | Q1 2025 | Karyn Butts and Erin Arneson | Complete | Researched coalition questions about existing campaigns to educate and motivate homeowners to select RRP certified contractors.
13 |  | Continue to narrow policy/system goals with coalition; Build buy-in for goals among partners and local officials | 1 presentation complete; 10 attendees engaged | Increased engagement with coalition; Increased consensus on policy/system changes needed | Q2 2025 | Karyn Butts and Erin Arneson | In Progress | Created decision making rubric for coalition to aid them in prioritizing a housing quality improvement goal.
14 |  | Select policy and system change goal with coalition | 1 goal identified with associated assets and barriers | Increased engagement with coalition; Increased consensus on policy/system changes needed | Q2 2025 | Karyn Butts and Erin Arneson | Planning
15 |  | Develop tools to support policy/system change goal, including plan to evaluate success | 3 tools developed (educational packet; code enforcement report template to document chipping and peeling paint to be addressed; evaluation plan) | Increased community capacity for policy/system changes | Q2 2025 | Karyn Butts and Erin Arneson | Not Started
16 |  | Pilot test policy/system change goal | 10 buildings complete pilot | Increased consensus on policy/system changes needed | Q3 2025 | Karyn Butts and Erin Arneson | Not Started
17 |  | Offer free Renovation, Repair and Painting classes quarterly to rental property owners | 1 class offered quarterly; 3 attendees recruited per quarter | Increased consensus on policy/system changes needed | Q3 2025 | Karyn Butts and Erin Arneson | Not Started
18 |  | Assess success of pilot and revise as needed | 1 meeting with code enforcement completed; Changes to system documented | Increased community capacity for policy/system changes | Q4 2025 | Karyn Butts and Erin Arneson | Not Started
19 |  | Expand pilot to one census block group | ~20 residential buildings visited and assessed for chipping and peeling paint | Increased buildings identified with chipping and peeling paint and educational resources for property owners to proactively address it | Q4 2025 | Karyn Butts and Erin Arneson | Not Started
GOAL | Housing Quality Improvement Policy and Systems Change Goal | In partnership with local code enforcement, create systematic proactive visual inspection for chipping and peeling paint of all rental properties every three years, including written report on issues and recommended actions provided to property owner. Code enforcement to provide rental property owner education on essential maintenance practices and offer free RRP training to all rental property owners.
20 | Property Owner Education | Develop property owner education tool about RRP training availability | 1 flyer created | Increased property owners trained in and utilizing RRP principles | Q1 2025 | Erin Arneson | Complete | Borrowed flyer template for another Community Partner.
21 |  | Send mailing to property owners from municipal rental registration list | Mailing to 200 property owners sent | Increased property owners trained in and utilizing RRP principles | Q2 2025 | Erin Arneson | In Progress | Identified neighborhoods to target using Maine Tracking Network data. Requested property owner addresses in the targeted area from municipal partner.
22 |  | Partner with RRP trainer to offer one RRP course per quarter. | 3 classes offered | Increased property owners trained in and utilizing RRP principles | Q2-4 2025 | Karyn Butts | Planning | Scheduled meeting with local RRP provider to discuss cost and logistics.
23 |  | Evaluate number of property owners attending due to mailing or referral from code enforcement | 1 summary of referrals to class compeleted | Increased property owners trained in and utilizing RRP principles. Increased property owners proactively addressing chipping and peeling paint | Q4 2025 | Karyn Butts | Not Started
24 | Facilitated Lead Dust Testing | Encourage partners (Community Health Workers, Head Start home visitors etc) to attend facilitated lead dust testing training | 10 partners contacted about training opportunity | Increased capacity for facilitated lead dust testing | Q1 2025 | Erin Arneson | Complete | Emailed 12 partners about training opportunity. Discussed with Head Start staff in collaboration meeting. |  | • 2 partners recruited
25 |  | Attend facilitated lead dust testing training | 2 staff attended training | Increased capacity for facilitated lead dust testing | Q1 2025 | Erin Arneson | Complete |  |  | • 2 staff trained
26 |  | Complete facilitated lead dust testing with families (see family education and faciliated lead dust testing above) | Complete 20 home visits to faciliate lead dust test kits with families in high risk neighborhoods | Increased number of families completing lead dust testing; Increased lead dust identified and addressed | Q1 2025 | Erin Arneson | Not Started
27 | Partner with Primary Care Providers re: Screening | Propose and secure partnership with primary care provider office | 2 offices contacted; 1 office engaged | Increased strength of partnerships with healthcare organization(s) | Q1 2025 | Erin Arneson | Complete | Family Medical Partners did not have capacity for project. Presented to Pediatric Smiles practice and they are interested. They provided their workflow and asked for educational materials for their waiting room.
28 |  | Assess opportunity to link families to free transportation for confirmatory testing | Local resources documented | Increased community capacity for improving blood lead testing rates | Q1 2025 | Erin Arneson | Complete | Identified transportation resource list to provide Medical Assistants who call to remind families to complete their venous confirmatory testing.
29 |  | Review practice workflow using technical asssitance from CLPPP | 1 workflow reviewed | Increased staff capacity for lead blood testing projects | Q2 2025 | Erin Arneson | In Progress | Provided workflow to CLPPP for review.
30 |  | Provide feedback on workflow to practice | Feedback provided | Increased practice capacity for improved blood lead testing. Increased number of children age 1 and 2 who complete a blood lead test and timely confirmation testing | Q2 2025 | Erin Arneson | Not Started
31 |  | Assess impact of revised workflow | 1 meeting with primary care office completed; improvements in blood lead testing documented | Increased number of children age 1 and 2 who complete a blood lead test and timely confirmation testing | Q4 2025 | Erin Arneson | Not Started
32 | Seeking Funding | Apply for funding from philanthropic organizations to support a local safe housing summit | 1 grant application submitted | Increased funding available for convening and engaging partners and to draw earned media attention | Q2 2025 | Karyn Butts | Planning | Identified grant opportunity. | Grant appears very competitive.
33 |  | Identify potential opportunities to embed lead poisoning activities into city HOME funding | 1 lead poisoning prevention activity added to city HOME workplan | Improved leveraging of local housing funding for lead hazard reduction | Q3 2025 | Karyn Butts | Planning | Requested meeting with Planning Department to discuss their HOME funding priorities.
34 | Participate in local housing collaboratives | Join Sewall Foundation housing collaborative | Quarterly meeting participation; create relationship with 3 new property owners | Strengthened partnerships with property owners | Q2-4 2025 | Erin Arneson | In Progress | Attended first meeting. Identified 3 members to connect with outside of regular meetings.
35 |  | Participate in municipal housing committee | Quarterly meeting participation; create relationship with 3 new property owners | Increased collaboration with code enforcement; Increased community capacity for policy/systems change | Q1-4 2025 | Erin Arneson | In Progress | Met with property owner who is interested in educating other landlords about need for proactive maintenance to avoid abatement orders. | Meetings are not well facilitated.
36 |  | Convene safe housing summit | Summit convened; 1 earned newspaper article | Increased awareness of lead poisoning among families, partners, and community leaders | Q3 2025 | Erin Arneson | Planning
37 |  | Integrate outcomes from safe housing summit into Foundation-led housing collaborative and municipal housing committee | 2 activities integrated into municipal housing committee efforts | Increased community capacity to address lead poisoning | Q4 2025 | Erin Arneson | Not Started
Note: All additional activities are represented here to provide workplan examples and ideas. The contract Rider A requires Community Partners to implement at least one additional activity. See Contract Deliverables tab or Rider A.

## EXAMPLE Logic Model
Staffing | Engagement | Engagement | Engagement
Partners / Collaborative | Connect with community leaders, partners, property owners and families | # Partners and Committees engaged | Increased strength, diversity and number of partnerships | Increased use of lead hazard prevention strategies (safer renovations, essential maintenance, etc) | More children without detectable blood lead levels
Trainings | Education | Education | Education
Technical Assistance | Provide awareness-raising, education and skill-building activities to community leaders, partners, property owners and families | # Trainings provided (# organizational attendees; # attendees) | Increased awareness, knowledge and skills of staff, partners, property owners and families | Increased number of lead hazards identified | Safer housing
Maine Tracking Network data |  | # Media campaigns implemented (reach, impressions etc) | Capacity
Evaluations and Best Practices | Capacity | Capacity | Increased capacity for lead poisoning prevention activities | Increased action to address lead hazards (abatement, mitigation)
| Leverage existing resources and seek new resources to address lead poisoning | # Grant applications completed | Increased consensus on policy/system changes needed
| Policy and Systems | # New funding sources identified / existing funding sources better leveraged | Policy and Systems | Increased blood lead testing; Case Management reaching families and homes most in need
| Identify and address gaps in lead poisoning prevention policies/systems | Policy and Systems | Policy and system improvements considered and implemented
| Evaluation | # Policy and system change ideas researched and presented | Evaluation | Increased use of evaluation to drive future innovations
| Assess successes and challenges | Evaluation | Evaluation data integrated into lead poisoning prevention efforts
# Evaluation activities completed
| Example Specific Short-Term Outcomes | The Short-term Outcomes above are intentionally broad. Please create more specific outcomes in your proposed workplan, such as:
Increased capacity for implementing lead poisoning prevention media campaigns
Increased knowledge of lead dust as the primary source of childhood lead poisoning in Maine
Increased awareness of essential maintenance practices as a means of reducing lead hazards in homes
Increased provider knowledge of state blood lead testing guidelines
Increased strength of partnership with municipal planning department
Increased number of funding streams supporting local lead poisoning prevention activities
Increased use of evaluation data to inform coalition activities

## REFERENCE Contract Deliverables
| Deliverable Category | Deliverable Description
REQUIRED | 1. Community Capacity Self-Assessment | • Conduct a local Community Capacity Self-Assessment within the ninety (90) calendar days of the start of the initial period of performance and annually thereafter.
| 2. Coalition Engagement | • At least annually, engage a coalition (i.e., board, advisory committee, or partner group based in the proposed service area), around childhood Lead Poisoning to provide local insights, guide service development, and build local buy-in related to Lead Poisoning prevention.
i. The group may be existing or those convened for the purpose of Lead Poisoning prevention.
ii. Membership shall include representatives from diverse sectors, or those with lived experience, related to Lead Poisoning risk factors or impacts (i.e., poverty, housing, public health, immigrant/refugee services, local government, social services, advocacy healthcare, etc.)
iii. Ensure the engaged coalition: 1. Reviews local data on Lead Poisoned children, screening rates, and housing related risk factors using Department provided data found on the Maine Tracking Network. 2. Reviews results from the local Community Capacity Self-Assessment. 3. Reviews a draft work plan, developed by the Provider, which addresses local childhood Lead Poisoning rates and incorporates this contract’s services c, d and e. The Provider will then submit a revised work plan to the Dept.
| 3. Family Education: | • Provide Lead Poisoning prevention education to families with children under six (6) years of age living in pre-1950 housing. Prioritize education to families who experience higher rates of Lead Poisoning on a population level (families with low income, families utilizing MaineCare services, families who identify as racial and ethnic minorities, and immigrant, refugee, and asylum-seeking families). Family education shall be provided to all municipalities in the proposed Service Area according to the Provider’s approved work plan and shall include:
i. Education and/or training on how to identify potential Lead Hazards in the home and how to keep children safe from lead.
ii. Encouraging parents to perform Home Lead Dust Testing
iii. Encouraging parents to have children tested for Lead Poisoning. Provide Lead Poisoning prevention education to families with children under six (6) years of age living in pre-1950 housing. Prioritize education to families who experience higher rates of Lead Poisoning on a population level (families with low income, families utilizing MaineCare services, families who identify as racial and ethnic minorities, and immigrant, refugee, and asylum-seeking families).
| 4. Housing Quality Improvement Policy/Systems Change | • Create and implement a process for identifying and building consensus for a local policy or system change goal that increases equitable access to and availability of lead-safe housing using results from the local Community Capacity Self-Assessment.
i. The timeline for achieving the policy or system change goal shall range between two (2) and five (5) years, depending on the complexity of the goal. In the work plan, the Provider shall identify activities they will complete under this Agreement that will lead to the policy or system change goal.
ii. Policy and system change efforts may include but not be limited to:
1. Creating more equitable access to lead-safe housing.
2. Providing education and meaningful incentives for rental property owners to utilize Essential Maintenance Practices.
3. Identifying barriers rental property owners experience to utilizing Lead Hazard control funds and creating a plan to address those barriers.
4. Creating a new municipal-level incentive program for property owners to proactively address Lead Hazards in their properties.
5. Requiring property owners to identify and address Lead Hazards in their rental units.
6. Strengthening local building codes and related inspection processes and/or increasing building code enforcement.
7. Identifying and creating a plan to address housing discrimination that limits access to lead safe housing.
8. Creating a system for municipalities to provide frequent and consistent Renovation, Repair, and Painting rule education to rental property owners.
9. Supporting local collaboratives or tenant groups to systematically test rental units for Lead Hazards and/or providing tenants with tools to discuss such hazards with their landlords or local leaders.
10. Other systems or policies that proactively address Lead Hazards in pre-1950 housing with a focus on rental properties.
ADDITIONAL SERVICES (Implement at least 1) | 5. Property Owner Education | • Provide Lead Poisoning prevention education to property owners of rental properties built before 1950 through at least one (1) of the following strategies:
i. Provide education and/or training on how to identify potential Lead Hazards in the home and how to keep children safe from lead.
ii. Provide education on lead disclosure laws and the Renovation, Repair and Painting rule.
iii. Encourage property owners to perform Home Lead Dust Testing
iv. Connect property owners to available local and State resources for lead abatement.
| 6. Facilitated Lead Dust Testing | • Offer Facilitated Lead Dust Testing to families living in pre-1950 housing, prioritizing families who experience higher rates of Lead Poisoning on a population level, such as families with low income, families utilizing MaineCare services, families who identify as racial and ethnic minorities, and immigrant, refugee, and asylum-seeking families. Home Lead Dust Testing kits may be ordered for free from the Department.
| 7. Primary Care Partnership for Screening | • Partner with primary care practices serving children under six (6) years old to review data on lead screening practices and discuss a plan for increasing practice screening rates.
| 8. Seeking Additional Funding | • Seek funding or other support from private or public sources to expand or complement Lead Poisoning prevention activities funded by the Department.
| 9. Convening or Participating in Housing Collaboratives | • Convene or participate in local housing-related community collaboratives with a stated goal in line with creating accessible and affordable safe housing.

## DropDownList (hidden)
Not Started
Planning
In Progress
Complete
Please do not edit this worksheet. It is the source data for programming drop down lists in the Workplan Reporting tab.